T-REX

Time-Resolving Explorer

Six-Month Mission Concept Maturation Strategy

August 2026 - January 2027

Purpose Organize the T-REX team around four integrated workstreams - hardware, software, theory, and proposal development - and convert the concept into a controlled, quantitative, reviewable mission package.

Prepared as a GitHub-centered team operating plan

Version 0.1 | 1 August 2026

# Executive Summary

T-REX is a proposed time-domain space-VLBI observatory intended to observe black holes, binary black-hole candidates, AGN jets, and millimeter transients as evolving systems. The supplied ASTRA concept uses deployable DiskSats, a central Pez bus, local 86 GHz recording, rendezvous/docking, centralized correlation, and downlink. It identifies timing synchronization, pointing, docking, reflector deployment, onboard storage, correlation, and communications as principal design drivers. [S1]

A second supplied note introduces a dual-mode architecture in which 18 hexagonal DiskSats either disperse to create long interferometric baselines or interlock into a larger collecting aperture. It gives a 0.715 m segment circumradius, 150 K system temperature, 0.65 aperture efficiency, a single-segment SEFD near 4.8e5 Jy, and an 18-segment SEFD near 2.7e4 Jy. [S2]

Core strategic recommendation Treat T-REX as a layered architecture: (1) a flight-demonstration technology payload, (2) a Pioneers-class pathfinder with bounded standalone science, (3) a SMEX-class initial observatory, and (4) a longer-term strategic reconfigurable array. This prevents one configuration from being forced to satisfy incompatible cost, maturity, and science objectives.

## The six-month outcome

One controlled reference mission and one explicitly descoped pathfinder.

A science-to-requirements traceability matrix with reproducible performance calculations.

A preliminary SWaP-C allocation and mission-class argument.

An orbit/baseline trade spanning LEO, high-apogee, and cislunar options.

One bench-level hardware or data-system demonstration.

A tested analysis package for SEFD, thermal noise, timing, data volume, angular resolution, temporal cadence, and orbit trades.

Proposal-ready packages tailored separately to ASTRA, NIAC, Flight Opportunities/TechLeap, Pioneers, and SMEX.

Student work packages tied to credit, UTRA/SPRINT, posters, papers, presentations, hardware/software ownership, and possible invention disclosures.

## Immediate management decision

The source documents contain at least two different architecture baselines: the ASTRA ConOps references a five-DiskSat constellation, while the dual-mode note uses 18 interlocking segments. The team should not merge these informally. Month 1 must define a Pathfinder Baseline, an Initial Science Mission Baseline, and a Strategic Architecture Baseline.

## Document conventions

| Label | Meaning |
| --- | --- |
| Source baseline | Directly supported by one of the supplied documents or an official program source. |
| Proposed | A recommendation for team organization or concept maturation. |
| Assumption | A numerical placeholder that must be reviewed and version-controlled. |
| Open issue | A contradiction, uncertainty, or feasibility question that cannot yet be closed. |

# 1. Mission Baseline and Configuration Control

## 1.1 Source-derived mission proposition

The source concept proposes a modular time-domain VLBI observatory. DiskSats deploy from a Pez spacecraft, independently observe black holes and jets with deployable reflectors, record data locally, and later transfer data to the Pez for correlation and downlink. The science narrative prioritizes Sgr A*, M87*, supermassive black-hole binaries, and time-variable AGN/transient phenomena. [S1]

## 1.2 Architecture branches

| Branch | Description | Best role | Primary concern |
| --- | --- | --- | --- |
| A: Pez + 5 DiskSats | Follows the ASTRA ConOps figure and distributed observing concept. | Initial constellation or pathfinder study. | Sensitivity, timing, data handling, and docking still demanding. |
| B: 18 interlocking DiskSats | Follows the dual-mode note; dispersed for baseline, combined for collecting area. | Long-term strategic architecture. | Surface accuracy, assembly, metrology, thermal control, and cost. |
| C: Minimal precursor | One DiskSat with ground VLBI, or Pez + 2-3 DiskSats. | Pioneers or flight-demonstration pathway. | Reduced angular coverage and science breadth. |

## 1.3 Recommended layered mission family

1.  Technology demonstrator: validate one enabling function such as precision timing, deployment, modular docking/interlocking, or high-rate data handling.

2.  Pioneers-class pathfinder: deliver one compelling astrophysics measurement while proving a small subset of the distributed architecture.

3.  SMEX-class initial observatory: field a more complete multi-element array with credible reserves, heritage, and operations.

4.  Strategic T-REX: develop the full reconfigurable dual-mode architecture through ASTRA-style concept maturation.

## 1.4 Gating open issues

| ID | Question | Six-month closure product |
| --- | --- | --- |
| OI-001 | Is the baseline 5, 18, or a staged family? | Approved architecture decision record and configuration matrix. |
| OI-002 | Can the system meet the >40 mJy and sub-minute science claim? | Source-specific sensitivity/cadence analysis. |
| OI-003 | Where does correlation occur and what data are moved? | End-to-end data-flow and storage/downlink budget. |
| OI-004 | Is 86 GHz the baseline, or is 230-690 GHz in scope? | Band roadmap with surface, receiver, timing, and thermal implications. |
| OI-005 | LEO, high-apogee, or cislunar? | Common orbit/science/cost/radiation trade. |
| OI-006 | Is docking essential? | No-docking fallback and staged demonstration plan. |

# 2. Six-Month Integrated Roadmap

The roadmap runs from August 2026 through January 2027. Each month ends with a review that integrates all four workstreams. The objective is evidence-based convergence, not simply producing more slides.

| Month | Integrated objective | Critical deliverables | Review gate |
| --- | --- | --- | --- |
| 1 - Aug 2026 | Baseline and team formation | Leads appointed; source/assumption registers; pathfinder and reference mission 0.1; first calculations; ASTRA workshop package; immediate TechLeap go/no-go. | Baseline Definition Review |
| 2 - Sep 2026 | Requirements and feasibility | Science traceability; target scenarios; timing/data/link budgets; LEO/high-apogee/cislunar comparison; initial risks; Ad ASTRA feedback. | Science & System Requirements Review |
| 3 - Oct 2026 | Architecture trades | Parametric SWaP-C; dispersed/clustered/combined modes; uv coverage; data/correlation architecture; reflector and clock downselect; Pioneers/SMEX boundary. | Architecture Trade Review |
| 4 - Nov 2026 | Demonstration and external review | Bench test; end-to-end simulated observation; external review; NIAC technology-study draft; Flight Opportunities payload draft. | Technology Demonstration Review |
| 5 - Dec 2026 | Convergence and proposal package | Closed actions; cost-class story; ConOps; six-slide deck and appendix; paper/poster/abstract drafts; invention screen. | Proposal Red-Team Review |
| 6 - Jan 2027 | Concept maturity and next phase | Mission Concept Package 1.0; reproducibility audit; maturity review; 12-month roadmap; Spring/Summer student assignments. | Concept Maturity Review |

## 2.1 Review criteria

No architecture decision is accepted without a requirement impact and risk impact.

No performance number is accepted without units, assumptions, a reproducible calculation, and a named reviewer.

No funding opportunity is treated as the mission architecture; the concept is tailored to the program, not redesigned by slide title.

No student task is accepted without a bounded deliverable, mentor, verification method, and communication output.

## 2.2 Team cadence

| Cadence | Purpose | Output |
| --- | --- | --- |
| Weekly workstream standup - 30 min | Local execution and blockers. | Updated issues and owners. |
| Weekly systems integration - 60 min | Interfaces, assumptions, requirements, and cross-workstream decisions. | Decision candidates and integration actions. |
| Biweekly technical review - 60 min | Calculation, design, simulation, or test deep dive. | Reviewed artifact and action list. |
| Monthly gate review - 90 min | Approve baseline maturity and next-month scope. | Review record and configuration update. |

# 3. Workstream Plans

## 3.1 Hardware Development

Hardware owns the physical credibility of the mission: antenna/reflector, receiver, thermal approach, timing reference, ADCS, storage, docking or crosslink, Pez interfaces, propulsion, power, and communications.

| Work package | Month 1-2 | Month 3-4 | Month 5-6 |
| --- | --- | --- | --- |
| Reflector/deployment | Trade membrane, mesh, and CFRP; define frequency-dependent surface tolerance. | Downselect; coupon/deployment breadboard; metrology concept. | Measured performance, risks, and maturation roadmap. |
| Receiver/thermal | Define 86 GHz chain, bandwidth, polarization, Tsys budget. | Bench architecture and component/thermal model. | Payload budget and verification plan. |
| Timing/frequency | Compare local USO, shared time transfer, hybrid/fringe-fitting. | Phase-coherence breadboard or high-fidelity simulation. | Clock/time-transfer allocation and test evidence. |
| ADCS/metrology/orbit determination | Pointing and relative-state requirements. | Sensor/actuator/metrology trade. | Closed-loop simulation and error budget. |
| Docking/servicing/interfaces | Define necessity, capture geometry, and alternatives. | Mockup or interface demonstration; no-docking fallback. | Reliability and operations concept. |
| Power/propulsion/communications | First budgets and transfer options. | Integrated SWaP-C and link model. | Pathfinder and SMEX allocations with reserves. |

## 3.2 Software Development

Software owns the digital engineering thread and must turn every critical claim into a repeatable analysis. The accompanying repository already includes tested first-order functions for sensitivity, resolution, timing, and data payload.

| Product | Acceptance criterion |
| --- | --- |
| Mission calculator | Reproduces source SEFD values and publishes assumption-controlled trade tables. |
| Orbit/visibility/uv tool | Generates target visibility, baseline evolution, and uv coverage for each orbit family. |
| Synthetic observation pipeline | Produces representative visibilities/light curves from a target model and orbit. |
| Correlation/data-flow prototype | Demonstrates recorder metadata, time tags, transfer, correlation, and reduced products at scaled bandwidth. |
| Automated reporting | Builds figures/tables from versioned inputs; tests run in GitHub Actions. |

## 3.3 Theoretical Development

Theory owns the conversion from broad science motivation to measurable correlated flux, variability, polarization, angular scale, cadence, and parameter-estimation requirements.

Construct source-specific models for Sgr A*, M87*, at least one PTA-relevant SMBHB candidate, and one transient/jet case.

Distinguish total flux from correlated flux on the baselines that T-REX actually samples.

Quantify the cadence and observing duration required to distinguish MAD and SANE variability signatures.

Model interstellar scattering, refractive noise, calibration error, and sparse coverage as science-systematics terms.

Produce end-to-end parameter estimates or detection statistics, not only illustrative images.

## 3.4 Proposal Development

Proposal development owns program fit, narrative, stakeholder engagement, graphics, review discipline, cost-class framing, student pathways, and proposal-ready boilerplate. It should not independently invent technical values.

Maintain a reusable mission narrative and a program-specific one-page summary for each pathway.

Keep a partner and reviewer map spanning mm-VLBI, spacecraft systems, timing, communications, formation flight, and cost.

Run red-team reviews with explicit evaluation criteria.

Coordinate public disclosure, authorship, acknowledgments, and possible intellectual-property review.

# 4. Critical Mission Parameters and Preliminary Calculations

The table below is a first-order baseline produced from the supplied dual-mode assumptions plus clearly labeled placeholders: 8 GHz processed bandwidth, two polarizations, two-bit real sampling, and 0.88 correlation/quantization efficiency. These are not final requirements.

| Parameter | Formula / assumptions | Preliminary result | Decision implication |
| --- | --- | --- | --- |
| Single-segment area | Regular hexagon, circumradius 0.715 m. | 1.328 m2 | Confirms the area stated in the dual-mode note. |
| 18-segment area | 18 times single area. | 23.91 m2 | Combined mode pools collecting area but needs precision assembly. |
| SEFD - single | 2 k Tsys/(eta A), Tsys=150 K, eta=0.65. | 4.80e5 Jy | Individual space-space baselines are sensitivity-limited. |
| SEFD - combined | Same relation, 18 segments. | 2.67e4 Jy | 18 times lower SEFD; observing geometry must define how this mode is used. |
| Thermal noise - single/single | 8 GHz, 60 s, efficiency 0.88. | 0.556 Jy (1 sigma) | Not consistent with 40 mJy at high SNR in one minute without additional sensitivity. |
| Thermal noise - single/single | 8 GHz, 10 h. | 22.7 mJy (1 sigma) | A 40 mJy correlated signal is only about SNR 1.8 on one identical baseline. |
| Thermal noise - combined/combined | 8 GHz, 60 s. | 30.9 mJy (1 sigma) | Would require two combined apertures for a long baseline; not the current single-cluster concept. |
| Raw data rate per element | 2 pol x 2 bits x 2B, B=8 GHz. | 64 Gbit/s | Dominant storage/crosslink/downlink driver. |
| Raw volume per element | 64 Gbit/s for 10 h. | 288 TB | For 18 elements: 5.18 PB before overhead; onboard reduction is likely essential. |
| Angular resolution | lambda/B at 86 GHz, B=12,000 km. | 59.9 uas | LEO/terrestrial-scale baseline does not reach a few uas at 86 GHz. |
| Angular resolution | lambda/B at 86 GHz, B=100,000 km. | 7.19 uas | High-apogee baselines materially improve 86 GHz resolution. |
| Angular resolution | lambda/B at 690 GHz, B=100,000 km. | 0.90 uas | Higher frequency tightens reflector, pointing, timing, and thermal requirements. |
| 90% coherence time error | C=exp(-sigma_phi^2/2), sigma_phi=2 pi f sigma_t. | 0.850 ps at 86 GHz; 0.106 ps at 690 GHz | A complete Allan-deviation/time-transfer/fringe-fitting model is a top priority. |

Critical sensitivity finding The source goal of sensitivity above 40 mJy and sub-minute temporal resolution is not yet demonstrated by the individual DiskSat assumptions. The team must model correlated source flux, ground-station pairings, array combination, bandwidth, Tsys, aperture, calibration loss, and required SNR before repeating this claim.

## 4.1 Dual-mode scaling issue

The dual-mode note correctly states that SEFD improves by a factor of 18 when collecting area increases by 18. It then states that the same SNR is reached in 1/18 of the integration time. Under the standard radiometer relation, fixed-SNR integration time scales as SEFD squared, which would imply a factor of 18 squared (324) when all other assumptions and observing geometry are unchanged. This should be resolved explicitly rather than silently edited. [S2]

## 4.2 Required calculation products

SEFD and baseline noise across frequency, aperture, bandwidth, Tsys, polarization, and ground-station pairings.

Temporal resolution as a derived SNR-and-calibration quantity, not an isolated requirement.

USO/time-transfer requirement expressed through Allan deviation, phase noise, coherence loss, orbit error, and fringe-fitting capability.

Data products by stage: raw samples, channelized data, visibilities, calibration, housekeeping, and selected raw snippets.

Angular resolution and imaging fidelity across evolving uv coverage.

Orbit visibility, baseline evolution, eclipses, radiation exposure, communications, and transfer duration.

# 5. Orbital Configuration and Concept of Operations

## 5.1 Nominal operational sequence

1.  Launch Pez and stowed DiskSats into a parking orbit.

2.  Commission Pez communications, navigation, timing, propulsion, and power.

3.  Deploy and commission DiskSats sequentially.

4.  Deploy reflectors and calibrate pointing, surface state, timing, and receiver response.

5.  Establish inter-satellite time transfer and relative orbit determination.

6.  Observe in dispersed space-VLBI, mixed space-ground VLBI, or a selected clustered/combined mode.

7.  Record and time-tag data locally.

8.  Transfer data through docking, RF/optical crosslink, or a hybrid approach.

9.  Correlate onboard Pez, in a distributed compute architecture, or on the ground.

10.  Downlink science products, recalibrate, reconfigure, and repeat.

## 5.2 SMART-1-style low-thrust analog

A T-REX high-apogee option could use solar-electric propulsion to raise apogee gradually, trading transfer speed for propellant efficiency. SMART-1 is a useful analog because it used solar-electric propulsion to spiral from a geostationary transfer orbit to lunar capture over roughly thirteen months and used only 82 kg of xenon; its average effective specific impulse was approximately 1540 s. [S9]

Important distinction SMART-1 began in GTO, not a 300-500 km LEO parking orbit. Its thirteen-month spiral should therefore be treated as architectural heritage, not a T-REX transfer-time estimate. A LEO-origin spiral must separately model delta-v, thrust arcs, power, eclipses, radiation-belt residence, navigation, and mission operations.

## 5.3 Orbit trade matrix

| Option | Science advantage | Engineering advantage | Primary penalty | Six-month analysis |
| --- | --- | --- | --- | --- |
| LEO | Frequent ground contact; rapidly changing short baselines. | Simpler launch/operations and lower latency. | Limited 86 GHz angular resolution; atmospheric/ground geometry dependence. | Target visibility, uv coverage, conjunctions, downlink. |
| High-apogee Earth orbit | Longer baselines and broad baseline evolution. | Remains Earth-centered; flexible apogee selection. | Radiation, communications, thermal/eclipses, transfer time. | Direct vs electric vs hybrid transfer and dose. |
| Cislunar/lunar-distant | Very long baselines and distinctive uv coverage. | Potential long-term strategic architecture. | Cost, navigation, latency, power, communications, mission class. | Science gain per cost/risk relative to high apogee. |

## 5.4 ConOps decision questions

Must DiskSats physically return to Pez, or can crosslinks eliminate repeated docking?

Can Pez correlate all elements within its power and thermal budget?

Does combined mode require physical interlocking, coherent phasing without contact, or neither?

How are clocks calibrated before, during, and after an observing pass?

What happens after one DiskSat fails, misses rendezvous, or cannot deploy its reflector?

Which science is possible during the transfer phase?

# 6. Funding and Program Strategy

The programs below occupy different levels of the maturation ladder. They should form a portfolio rather than being presented as interchangeable funding sources.

| Program | What it is | Best T-REX fit | Near-term product |
| --- | --- | --- | --- |
| ASTRA | NASA Astrophysics initiative to identify and develop early strategic mission concepts and advance them ahead of formal pre-Phase A. [S3] | Strategic architecture, community alignment, and Concept Maturity Level discipline. | Workshop engagement, six-dimension maturity package, strategic architecture trades. |
| NIAC | Staged studies of visionary, technically credible advanced concepts. Phase I studies explore viability over up to nine months. [S4] | One breakthrough enabling technology, not the complete science mission. | Technology thesis, feasibility questions, model/test plan, exit criteria. |
| Flight Opportunities / TechLeap | Commercial flight testing and challenge-based development of flight-ready payloads. The 2026 TechLeap challenge emphasizes robotic manipulation, modular assembly, and sensor deployment. [S5] | Docking/interlocking, deployable reflector segment, time-transfer payload, or modular interface demonstration. | Self-contained payload concept with interfaces and measurable flight success criteria. |
| Astrophysics Pioneers | Small astrophysics missions with a $20M cost cap. [S6] | Aggressively descoped pathfinder with standalone science. | Pathfinder science case, minimal constellation, cost/SWaP-C boundary. |
| SMEX | Competed Astrophysics Small Explorer mission class; the 2026 cost cap is $190M. [S7] | More complete initial observatory. | Reference mission with reserves, heritage, operations, team, and verification. |

## 6.1 Recommended three-track portfolio

1.  Strategic concept track: ASTRA and broader astrophysics community engagement.

2.  Technology track: NIAC plus Flight Opportunities/TechLeap or similar demonstrations.

3.  Mission track: Pioneers pathfinder leading toward a SMEX-class observatory.

## 6.2 Mission-class discipline

Pioneers should be treated as a hard design constraint for a reduced mission, not a label placed on the full 18-element architecture. Conversely, ASTRA is oriented toward strategic concepts and should not be used as proof that the architecture already fits a small-mission cap. The six-month study should show precisely what is delivered at each rung.

## 6.3 Proposal products by Month 6

One-page mission summary and two-page technical summary.

Science traceability matrix and critical parameter table.

Pioneers pathfinder concept sheet and SMEX reference mission sheet.

NIAC-style enabling-technology study outline.

Flight-demonstration payload concept with success criteria.

Partner/reviewer map and stakeholder briefing deck.

Reusable management, risk, schedule, and student-participation language.

# 7. Stakeholder Slide Structure

The requested six-slide structure is strong if each slide communicates a decision rather than merely listing topics.

| Slide | Decision question | Required content |
| --- | --- | --- |
| 1. SWaP-C Requirements | What version of T-REX fits Pioneers, and what requires SMEX? | Pathfinder versus reference mission; mass, power, cost, volume, schedule, reserves, and descopes. |
| 2. Critical Mission Parameters | Does the design close quantitatively? | SEFD, thermal noise, timing/USO, data payload, angular resolution, temporal resolution, orbit, coherence - each with formula, assumption, result, target, uncertainty. |
| 3. Preliminary ConOps | How does the observatory actually operate? | Launch/transfer, deployment, calibration, observing modes, recording, transfer, correlation, downlink, reconfiguration, failure response. |
| 4. Nominal Timeline | What happens next and what proves progress? | Six-month gate reviews plus longer concept, breadboard, flight demo, pathfinder, and mission pathway. |
| 5. Funding Opportunities | Which program funds which maturation step? | ASTRA, NIAC, Flight Opportunities/TechLeap, Pioneers, and SMEX placed on one ladder. |
| 6. Brown Student Opportunities | Why should students join and what will they own? | Credit, UTRA/SPRINT, papers, posters, conferences, patents/disclosures, hardware, software, proposals, stakeholder presentations. |

## 7.1 Slide design rule

One slide, one decision Each slide should contain one headline conclusion, no more than one main visual, and a small evidence panel. Detailed equations and trade tables belong in the technical appendix and repository.

## 7.2 SWaP-C table to build

| Element | Mass | Power peak/avg | Data/storage | Volume | Cost range | Maturity |
| --- | --- | --- | --- | --- | --- | --- |
| Pez bus | TBD | TBD | Correlation/downlink | TBD | TBD | TBD |
| DiskSat bus - each | TBD | TBD | Local recording | TBD | TBD | TBD |
| Reflector/deployment | TBD | TBD | Metrology data | TBD | TBD | TBD |
| 86 GHz payload - each | TBD | TBD | Raw/channelized | TBD | TBD | TBD |
| Timing/metrology | TBD | TBD | Phase/orbit metadata | TBD | TBD | TBD |
| Propulsion and transfer | TBD | TBD | Navigation | TBD | TBD | TBD |
| Ground segment/operations | N/A | N/A | Archive/compute | N/A | TBD | Heritage TBD |

# 8. Brown Student Opportunities and Team Governance

## 8.1 Student opportunity model

| Opportunity | How T-REX should structure it | Evidence of completion |
| --- | --- | --- |
| Academic credit | Independent study, capstone, thesis, or project course subject to faculty/department approval. | Reviewed technical artifact and final presentation. |
| Funding - UTRA/SPRINT | Faculty-student research collaboration with a bounded project description and mentor. UTRA supports Brown students collaborating with faculty. [S8] | Application package and funded work plan. |
| Paper | Methods, instrument concept, science forecast, orbit trade, or demonstration result. | Authorship plan, reproducible figures, draft manuscript. |
| Poster/conference | One technical question per poster or abstract. | Accepted abstract or symposium presentation. |
| Patent/invention disclosure | Screen genuinely novel mechanisms, timing approaches, interfaces, or algorithms before public disclosure. | Internal invention review; disclosure where appropriate. |
| Hardware development | Own a measurable breadboard or subsystem analysis. | Test report linked to requirement. |
| Software development | Own a tested module, simulation, pipeline, or dashboard. | Merged code, tests, documentation, and demo. |
| Proposal involvement | Own a section and its evidence package. | Reviewed text, figure, budget input, or schedule input. |
| Stakeholder presentation | Brief advisors, NASA/community groups, or partners. | Recorded feedback and action closure. |

## 8.2 Governance roles

Mission Lead: science vision, external representation, final decision authority.

Systems Integration Lead: requirements, assumptions, interfaces, reviews, and configuration control.

Hardware, Software, Theory, and Proposal Leads: workstream delivery and review quality.

Student Program Coordinator: onboarding, mentors, credit/funding alignment, and equitable ownership.

External Review Panel: periodic challenge of science, systems, timing, VLBI, and cost assumptions.

## 8.3 GitHub operating model

1.  Open an issue with the technical question, owner, assumptions, deliverable, and acceptance test.

2.  Develop on a workstream branch and link every quantitative output to code or a controlled spreadsheet/table.

3.  Request a reviewer outside the author's workstream.

4.  Record architecture decisions in an ADR and update affected requirements, risks, and slides.

5.  Merge only after tests pass and the artifact is reproducible.

## 8.4 Definition of done

Done means integrated A calculation, component study, or proposal paragraph is complete only when it changes or confirms a requirement, closes or reframes a risk, and is visible in the controlled mission baseline.

# 9. Month-6 Deliverable Package

| Deliverable | Owner | Acceptance criterion |
| --- | --- | --- |
| Mission Concept Package 1.0 | Systems + all leads | Consistent architecture, assumptions, requirements, ConOps, risks, SWaP-C, and program pathway. |
| Science Traceability Matrix | Theory | Every top-level requirement traces to a target/observable and analysis. |
| Critical Parameter Workbook/Code | Software | Reproducible, tested calculations with units and assumptions. |
| Hardware Architecture and Breadboard Report | Hardware | Subsystem interfaces, budgets, measured result, and maturation plan. |
| Orbit and Operations Trade | Hardware + Software | Common comparison of LEO, high-apogee, and cislunar concepts. |
| Pioneers Pathfinder Concept | Proposal + Systems | Standalone science, bounded mechanisms, preliminary cap compliance. |
| SMEX Reference Mission Concept | Proposal + Systems | More complete observatory with reserves, heritage needs, and verification plan. |
| NIAC Technology Study Outline | Hardware/Theory/Proposal | One transformative technology with feasibility questions and exit criteria. |
| Flight Demonstration Payload Concept | Hardware/Software/Proposal | Self-contained interfaces, environment, test objectives, and success metrics. |
| Six-Slide Stakeholder Deck + Appendix | Proposal | One decision per slide; all numbers trace to repository outputs. |
| Student Output Portfolio | Student coordinator | Named owners, credit/funding plans, paper/poster/presentation targets. |

# 10. First Two Weeks: Action List

1.  Name the Mission Lead, Systems Integration Lead, and four workstream leads.

2.  Create the GitHub repository from the accompanying scaffold and assign branch/review rules.

3.  Approve the three architecture labels: Pathfinder, Initial Science Mission, Strategic Architecture.

4.  Review every assumption in the baseline calculation output, especially bandwidth, polarization, quantization, and efficiency.

5.  Assign one theory student to correlated-flux target models and one software student to orbit/uv coverage.

6.  Select a hardware breadboard candidate and identify needed lab access.

7.  Prepare the Ad ASTRA workshop brief and a list of five questions for external experts.

8.  Make an immediate go/no-go decision on any active TechLeap pathway after verifying current registration and eligibility.

9.  Schedule the Baseline Definition Review before the end of August.

# Sources

[S1] T-REX: Time-Resolving Explorer - ASTRA Mission Concept, user-supplied PDF, 6 pages.

[S2] T-REX: A Dual-Mode DiskSat Constellation - Dispersed VLBI vs. Combined Single-Dish Sensitivity, user-supplied PDF, 1 page.

[S3] NASA, The Astrophysics Strategic Technology & Research Accelerator (ASTRA) Initiative: https://science.nasa.gov/astrophysics/programs/physics-of-the-cosmos/studies/astra-initiative/

[S4] NASA, NASA Innovative Advanced Concepts (NIAC): https://www.nasa.gov/stmd-the-nasa-innovative-advanced-concepts-niac/

[S5] NASA, Flight Opportunities and TechLeap Prize information: https://www.nasa.gov/stmd-flight-opportunities/ and https://www.nasa.gov/stmd-flight-opportunities/access-flight-tests/nasa-techleap-prize-information/

[S6] NASA Science, Astrophysics Pioneers: https://science.nasa.gov/astrophysics/programs/astrophysics-pioneers/

[S7] NASA Science, 2026 Astrophysics Small Explorer information: https://science.nasa.gov/astrophysics/programs/physics-of-the-cosmos/community/2026-astrophysics-small-explorer-announcement-of-opportunity/

[S8] Brown University, Undergraduate Teaching and Research Awards: https://utra.brown.edu/

[S9] European Space Agency, SMART-1 operations and electric propulsion records: https://www.esa.int/Enabling_Support/Operations/SMART-1_operations2

## Scope note

This strategy organizes concept maturation; it is not a flight design, cost estimate, safety certification, or program eligibility determination. Program schedules and rules should be checked against the current official solicitation before submission.